## SITCOM Workplan Information
2023 SITCOM Workplan
Use the tabs below to access the Statewide Training Priorities, Task Force Action Plans and Proposals.
How do we define interagency?
"Interagency" means going beyond what can be accomplished alone by individual agencies or areas. Interagency trainings are designed to appeal to a broader audience and are planned through coordination and collaboration of multiple entities.
What is a SITCOM training?
SITCOM promotes and supports the development and delivery of training. Individual or groups of members may develop training in coordination with outside members. SITCOM works to identify training needs and help potential trainers or training teams to coordinate the development and delivery of trainings.
What belongs in our workplan?
The SITCOM workplan serves to track the statewide training priorities, how SITCOM is planning to address each need, and task force proposals and action plans.

## Statewide Training Priorities
Statewide Training Needs
Stream, Shoreline, Lake, and Wetlands Management (46%, 145)
Interest | Topic | Points of Contact | Notes | Format | Time/Location | Status
29%, 97 | Shoreline Erosion, Riparian Buffers, Native Plantings, Stormwater Runoff, and HABs | Emily Micolichek, Stacy Dehne
26%, 88 | Stream Protection, Corridor Restoration, Evaluation Tools and Site Assessment | Luke Roffler | Luke Roffler has changed positions - need a new point of contact.
24%, 79 | Wetland Creation, Management, and Restoration | Luke Roffler | Luke Roffler has changed positions - need a new point of contact.
Farmstead, Cropland, and Nutrient Management (42%, 140)
Interest | Topic | Points of Contact | Notes | Format | Time/Location | Status
16%, 54 | Cover Crops | Mike Stanek (and many others) | Discussion w/ Mike Stanek - proposing incorporating this into the Conservation Training Bootcamp proposal.
Habitat, Plant, and Wildlife Management and Invasive Species (41%, 137)
Interest | Topic | Points of Contact | Notes | Format | Time/Location | Status
25%, 82 | Prairie & Grasslands Habitat, Pollinators, Plant Identification, and Establishment | Steve Bertjens (Mike Stanek) | Discussion w/ Mike Stanek - proposing incorporating this into the Conservation Training Bootcamp proposal.
24%, 79 | Riparian & Wetland Habitat, Plant Identification, and Restoration | Luke Roffler, Ducks Unlimited?, Ryan Glassmaker
Soil Health (33%, 109)
Interest | Topic | Points of Contact | Notes | Format | Time/Location | Status
15%, 50 | Seeding Rates, Mixes, and Application | Steve Bertjens (Mike Stanek, NRCS ARCs) | Discussion w/ Mike Stanek - proposing incorporating this into the Conservation Training Bootcamp proposal.
Community Engagement, Education, and Enforcement (42%, 140)
Interest | Topic | Points of Contact | Notes | Format | Time/Location | Status
22%, 73 | Raising Awareness and Educating the Public (Ecological Literacy) | Savanna Institute (Demo Farms), RC&D's | Variability of training possiblities
Emerging Planning Topics: Watershed and Climate Resiliency (32%, 108)
Interest | Topic | Points of Contact | Notes | Format | Time/Location | Status
17%, 58 | Climate Mitigation and Adaptation Strategies (mitigating climate impacts and preparing communities for extreme weather) | Christina Anderson Kristen Foehringer
Mapping and Design Tools (44%, 147)
Interest | Topic | Points of Contact | Notes | Format | Time/Location | Status
25%, 84 | ArcGIS | DNR GIS team?, Kelli Neitzel, Tony Reali | Might need to find out more specific needs related to participants, for example, if they need fieldtools vs basic functions (variability)

## Mentor-Cohort Task Force
Mentor-Cohort Task Force
SITCOM Members: Drew Zelle, Kevin Erb, Karl Gesch, Isabelle Paulse, Michael Hook
Non-SITCOM Members: Carolyn Pralle, Kirstie Heidenreich, Ketty Clow, Chad Trudell
Action Plan Status: Approved by SITCOM, June 2023
Challenge 1: Developing Operational Guidance
Why | What | Who | When | Status
Accurately representing the purpose and procedure of the Mentor/Cohort program will clarify the roles and expectations of participants and will help ensure that the program is operating as intended following the Task Force's efforts to gather input and feedback from staff across the landscape. | SITCOM will assemble of team to review the findings and recommendations of the Task Force, follow up with stakeholders to address any gaps related to procedure or outcome, and ultimately draft an operational guidance document that outlines the roles, expectations, guidelines, and procedures of the program. | Kirstie Heidenreich Ketty Clow Chad Trudell | Q3 2023 | In Progress
Obtaining feedback and approval from stakeholders, including participants and department/agency leaders, will ensure that the program will accurately represent and address the needs of all within the landscape. | SITCOM, along with agency/department leaders, will review the operational guidance draft, identify any areas for review or revision, and approve the draft to be used for the pilot program. | Kirstie Heidenreich Ketty Clow Chad Trudell | Q3 2023 | In Progress
Challenge 2: Conducting Pilot Program
Why | What | Who | When | Status
As SITCOM's partnership with agencies and departments has been essential for the development of this program, working in coordination to identify interested candidates for a pilot program will help the pilot best represent the full program. | SITCOM, following the procedure from the approved operational guidance, will coordinate with participating agencies and departments to identify candidates for the pilot program. These candidates, both mentors and mentees, will follow the onboarding procedures, and if appropriate, will be matched and begin their participation in the pilot. Number of candidates will be determined by operational guidance process. |  | Q4 2023
Before the full-fledged program can begin, a pilot program to test the operational guidance and determine areas for improvement must be conducted. | Program coordinators will work with candidates, both mentors and mentees to establish professional development plan goals, identify appropriate matches, and begin the process of coordinating schedules, meeting, and engaging in the mentorship program. |  | Q4 2023 through Q1 2024
Following the pilot program, participants within the program must be engaged to offer their feedback and guidance in order to determine any changes needed to the program if it is to move to full implementation for all Wisconsin staff. | SITCOM, along with program coordinators and participants will review the results of the pilot program and make recommendations for procedural changes as needed. If the pilot is considered a success, SITCOM will move to make any adjustments needed before moving to the full program implementation. |  | Q1 2024 (Before the Conference)

## Online Resources Task Force
Online Resources Task Force
SITCOM Members: Matt Woodrow, Dan Marzu, Isabelle Paulsen, Michael Hook
Non-SITCOM Members: Andrea Topper, Tom Boisvert, Kristin Teston, Beth Peterson (consulted)
Action Plan Status: Approved by SITCOM, June 2023
Challenge 1: Interagency File Sharing
Why | What | Who | When | Status
Providing all agency partners the ability access and share files relating to training and professional development will enhance interagency communication and coordination. | Wisconsin Land+Water will be updating their website and will explore adding Microsoft OneDrive and SharePoint as tools to create a shared files access point for employees from all agencies. | Michael Hook Kristin Teston Matt Woodrow | 2023 Q2-Q3 | In Progress
Hosting project resource galleries and databases will support LWCDs and agency partners who are looking to implement conservation practices in their areas. | Wisconsin Land+Water will coordinate with Technical Committee and the Standards Oversight Council to determine the most effective way to keep a regularly updated and accurate database and photo gallery for conservation projects and practices. | Michael Hook Kristin Teston Tom Boisvert | 2023 Q3 | In Progress
Challenge 2: Advertising and Supporting Partner Training Programs
Why | What | Who | When | Status
Effectively advertising and providing access for partner agency training programs will increase participants' ability to attend important training programs. | Wisconsin Land+Water will be updating their website, including a review of the training calendar, filtering, video hosting, and registration process. Training program leaders and users will be invited to provide feedback and insight in order to make appropriate changes. | Dan Marzu Andrea Topper | 2023 Q2-Q3 | In Progress
Coordinating agency and area team (AITCOM) access to data and information can help support more accurate training program planning and development. | (How can we provide better access to support materials like the Needs Assessment Survey?) Wisconsin Land+Water will be updating their website - having the ability for training programs, agency leaders, coordinators, and area teams (AITCOMs) to access the needs assessment data. Also, a SITCOM task force is proposed for the Fall to address how area teams access this information to identify training needs. | Matt Woodrow Mark Witecha? | 2023 Q3-Q4
Employee onboarding can often be a challenge, considering the many intracacies of how Wisconsin's professional conservation landscape operates. Buidling a coordinated and consistent support system for new hires will help all agencies streamline the process. | During Wisconsin Land+Water's website development and update, a focus group will be gathered to identify onboarding needs and materials from multiple partner agecies and departments in order to create a web-based resource page for new and incoming staff to acess. |  | 2023 Q4

## Future Task Force Ideas
Future SITCOM Task Force Ideas
Conservation Professional Interagency Bootcamp Training Series
Key Questions
Broad Conservation Knowledge:
What should all conservation professionals know from the wide array of conservation practices?
What should all conservation professionals experience in the field to support this knowledge?
Training Standards:
What does it mean to be a "well-trained conservation professional"?
What makes an effective conservation trainer, and how can SITCOM support their development?
What makes an effective training environment, and how can SITCOM support instructors to cultivate them?
AITCOM Operational Guidance Review
Key Questions
What makes an effective AITCOM, and how can SITCOM support each of them to achieve their goals?
When should AITCOMs have their meetings, establish their training plans, and submit their support requests?
Needs Assessment Analysis
Key Questions
How do we effectively interpret the findings from the Needs Assessment in order to best support our partners and programs?
What barriers exist that are supported by the Needs Assessment data, and how can SITCOM support partners and programs to overcome them?
Statewide Review Process
Engaging private sector and interagency reps to assess the review process for efficiency
(Problem - see notes, multiple reviewers and slowing down process, reviewers may have similar comments and could benefit from better coordination)